| Focus Area Content |  |  |  |
| --- | --- | --- | --- |
| Priority Focus Area: |  | Affordable Housing |  |
| Related Objective(s): Note: Must follow SMART+C formatting; Include data source (currently available or to be developed); Include frequency of data reporting - Is there an opportunity to develop an objective that is related to achieving equity? - SMART+C: Specific, Measureable, Achievable, Relevant, Timed & Challenging |  | By 2028, increase supply of affordable rental housing for households at 30-60%AMI by 1,500 new units. - increase supply of affordable units for households under 30%AMI by 375 (25%) new units - increase supply affordable units for households at 30-60%AMI by 1,125 (75%) new units - Of the above units, 75% will be 2-3 bedroom units By 2028, increase supply of affordable homeownership housing for homeowners at 40-80%AMI by 400 new units - increase supply of accessible, affordable units for seniors and people with disabilities at 30-80% AMI by 200. By 2028, develop a longer term housing strategic plan By 2028, establish system changes that right power imbalances preventing access to, or development of, affordable housing. |  |
| Planned Strategy 1: Prioritize incentives and subsidy for new development of units with 2-3 bedrooms |  |  |  |
| Action Steps for Strategy 1: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify lead agency or agencies to apply for and manage annual and special NOFO funding | TBD |  |  |
| Establish guidelines and procedures for incentives and subsidy | TBD |  |  |
| Establish a locally funded subsidy pool | Capital Acquisitions and Development workgroup |  |  |
| Identify additional funding sources | Capital Acquisitions and Development workgroup |  |  |
| Planned Strategy 2: Establish City of Lawrence Affordable Housing Overlay Zone to reduce cost and incentivize the development of affordable housing |  |  |  |
| Action Steps for Strategy 2: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Hold community meetings to champion zone and create buy-in | Low-Barrier Housing Case Management workgroup |  |  |
| Planned Strategy 3: Maintain existing affordable housing stock through the purchase of units coming out of affordability and putting in community land trust |  |  |  |
| Action Steps for Strategy 3: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify one-time funding source | Capital Acquisitions and Development workgroup |  |  |
| Identify on-going funding source | Capital Acquisitions and Development workgroup |  |  |
| Inventory existing housing that meets this criteria | Family Supportive Housing and Sheltering workgroup |  |  |
| Planned Strategy 4: Change development code to allow for increased density, height, minimum lot size, and multifamily units |  |  |  |
| Action Steps for Strategy 4: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Lobby local council regarding need for code changes | TBD |  |  |
| Present new code language to legislators | TBD |  |  |
| Planned Strategy 5: Remove development code stating that only three unrelated people can live together |  |  |  |
| Action Steps for Strategy 5: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Lobby local council regarding need for code changes | TBD |  |  |
| Present new code language to legislators | TBD |  |  |
| Planned Strategy 6: Establish tenant right to counsel |  |  |  |
| Action Steps for Strategy 6: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Create process establishing tenant right to counsel | TBD |  |  |
| Establish process for tenants to follow regarding right to counsel | TBD |  |  |
| Planned Strategy 7: Establish SOI protections and accountability measures |  |  |  |
| Action Steps for Strategy 7: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Establish outcomes and key performance indicators | TBD |  |  |
| Planned Strategy 8: Build capacity and funding for not for profit developers to develop in the Douglas County community |  |  |  |
| Action Steps for Strategy 8: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify one-time funding source | Capital Acquisitions and Development workgroup |  |  |
| Identify on-going funding source | Capital Acquisitions and Development workgroup |  |  |
| Planned Strategy 9: Ensure community engagement in the development of this plan and adjust as needed |  |  |  |
| Action Steps for Strategy 9: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Hold community meetings to champion zone and create buy-in | Low-Barrier Housing Case Management workgroup |  |  |
| Identify evidence-based practices essential to service models for supportive housing | Low-Barrier Housing Case Management workgroup |  |  |
| Develop community training and education sessions on supportive housing design and community integration from which the community may benefit | Low-Barrier Housing Case Management workgroup |  |  |
| Planned Strategy 10: |  |  |  |
| Action Steps for Strategy 10: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Planned Strategy 11: |  |  |  |
| Action Steps for Strategy 11: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |