AGENDA

Housing & Homelessness Stakeholders

Affordable Housing Workgroup

Thursday, June 22, 2023 | 10:00a-11:00a | Zoom
https://lawrenceks.zoom.us/j/91834799724?pwd=Qm9GOC9rc1ZvN1ZBcFY1Z2YyL1ErZz09

Present: Shannon Oury – LDCHA, Rich Minder – SB6, Lea Roselyn – City of Lawrence, Gabi Sprague – Douglas County, Kevyn Gero – City of Eudora, Mathew Faulk – Bert Nash, Shanae Eggert – KSHC, Gabby Boyle – Care Center, Dana Ortiz – FPL, Erika Zimmerman – Lawrence HFH, Emily Sharp – KHRC, Sara Taliaferro – Justice Matters, Steve Ozark – Justice Matters

| Time | Agenda Item |
| --- | --- |
| 10:00am | Introductions & Icebreaker |
| 10:10am | Review plan. Make commitments and assess for capacity |
| 10:40am | Discuss budget projections for the affordable housing strategies |
| 10:55am | Wrap-up/next steps |
| 11:00am | Adjourn |

10:10am	Review plan. Make commitments and assess for capacity

- Wednesday June 28th for County Commission

- Tuesday July 11th for City Commission

  - Goal with these two is to provide budget estimations, share what we learned through community engagement, and meeting emergency service needs

- Sometime this winter, going to the two commissions for approval, maybe December

- Objectives

  - 1500 affordable units might be too much of a stretch

    - Some thoughts

    - Need for a current inventory

    - Need for a budget analysis

  - Received feedback from national housing firm and partners

    - 30-60% AMI is too low

      - Affordability of the asset being more important

      - People pay a lot more in rent than mortgage

      - Systems and vehicles to afford the price

      - 30-60% AMI or 60-80% households aren’t made

- Number should reflect the need?

  - Need it to be aspirational

  - Need it to be doable

- Healthy ratio of homeownership and rentals?

- Dana, Erika, and Lea will parse up subsidy

- Strategy 1

  - AHAB

- Strategy 2

  - TTH, Habitat, LDCHA

  - Dana, Rebecca, Shannon

- Strategy 3

  - Already happening

- Strategy 4

  - Happening with DGCOHHS

- Strategy 5

  - Gabby Boyle can lead

- Strategy 6

  - Lot of concern from landlords, real estate agents, who profit off of speculation

  - Housing held in speculation, not to seize property, so we’re collecting money who are holding valuable housing stock

- Strategy 7

  - Put in a budget request for consultation, Lea can lead the group since it’s in her position.

  - AHAB, Lea, Sara, Erika

- Strategy 8

  - Melissa Nolte

- Strategy 9

  - AmeriCorps Member, City Comms, Kevyn Gero, County Comms

- Strategy 10

  - Lea/AHAB

- Strategy 11

  - Chip Blaser, DCCF, Sunflower Foundation

  - Get an endowment going?

    - Private housing folks paying into the AHTF fund somehow

    - How do we tax or get people to give back given their impacts on the market

  - Justice Matters (?)

- Strategy 12

  - Erika

    - LHFH can get support through the national organization who is leading an effort to increase Black homeownership

- Strategy 13

  - Wishlisted

- Strategy 14

  - Consideration of separating CHODO and CLT

  - Change to explore if we need additional CHODOs or CLTs

  - Erika will work with Lea to explore if we need additional CHODOs or CLTs

10:40am	Discuss budget projections for the affordable housing strategies

10:55am	Wrap-up/next steps

11:00am	Adjourn