| Housing Community Plan – Affordable Housing |  |  |  |
| --- | --- | --- | --- |
| Objective(s): |  | - By 2028, increase supply of affordable rental housing for households at 30-60%AMI by 1,500 new units. - increase supply of affordable units for households under 30%AMI by 375 (35%) new units - increase supply affordable units for households at 30-60%AMI by 1,125 (65%) new units - Of the above units, at least one-third will be 2-3 bedroom units - By 2028, increase supply of affordable homeownership housing for homeowners at 30-80%AMI by 400 new units - Increase supply of affordable HO units at 30-60% AMI by 200 (50%) - Increase supply of affordable HO unites at 60-80% by 200 (50%) - Increase supply of accessible, affordable units for seniors and people with disabilities at 30-80% AMI by 200. - Of the above units, 25% will be 4-5 bedroom units - By 2028, develop a 10-year affordable housing strategic plan - By 2028, establish system changes that realign power imbalances preventing access to, or development of, affordable housing |  |
| Planned Strategy 1: Provide grant subsidy for new development of units with 2-3 bedrooms |  |  |  |
| Action Steps for Strategy 1: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify organization or entity responsible for developing NOFO and managing affordable housing grants | Affordable Housing Advisory Board with community partners | Q3 2023 |  |
| Focused outreach with developers for discussions about incentives that would encourage/enable them to build units with 2-3 bedrooms and make at least 10% or more affordable. | Affordable Housing Advisory Board with community partners | Q3 2023 | Staff and volunteer time Budget for print materials |
| Identify lead agency or agencies to apply for and manage annual and special NOFO funding | Affordable Housing Advisory Board with community partners | Q4 2023 |  |
| Establish guidelines and procedures for incentives and subsidy Identify additional funding sources |  |  |  |
| Planned Strategy 2: Increase permanently affordable housing stock by identifying and acquiring parcels and units for the community land trust and future affordable housing development |  |  |  |
| Action Steps for Strategy 2: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Meet with Tenants to Homeowners/Community Land Trust, Habitat for Humanity, City of Lawrence, Douglas County, and stakeholders to determine housing development roles | Tenants to Homeowners, Habitat for Humanity and Lawrence-Douglas County Housing Authority | Q3 |  |
| Research current City HOME & CDBG priorities | Tenants to Homeowners, Habitat for Humanity and Lawrence-Douglas County Housing Authority | Q3 2023 | Staff time |
| Identify additional on-going funding source | Tenants to Homeowners, Habitat for Humanity and Lawrence-Douglas County Housing Authority | Q4 2023 | Staff time |
| Advocate for prioritization of locally allocated federal funds to be utilized for permanent affordability | Tenants to Homeowners, Habitat for Humanity and Lawrence-Douglas County Housing Authority | Q1 2024 | Staff and volunteer time |
| Planned Strategy 3: Provide recommendations to Land Development Code Update Steering Committee for code updates that allow for flexible, time-efficient and cost-effective affordable housing development. |  |  |  |
| Action Steps for Strategy 3 |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Meet with Planning Director to gain understanding of Land Development Code update process, timing, and influence points | Rebecca Buford & Lea Roselyn | Q1 2023 | Staff time |
| Determine the specific code updates to align for affordable housing land development code best practices (e.g. density, building typologies, ADUs, Shared Equity Ownership Models, etc.) | Rebecca Buford & Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q1 2023 | Staff and/or volunteer time |
| Provide input on Land Development Code update assessment | Rebecca Buford, Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q1 2023 | Staff and/or volunteer time |
| Write letter of recommended code updates to Land Development Code Update Steering Committee | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Q2 2023 | Staff and/or volunteer time |
| Regularly update Affordable Housing Workgroup on opportunities for ongoing engagement and communication for Land Development Code update | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Ongoing during Land Development Code update process (2023-2024) | Staff and/or volunteer time |
| Review and provide feedback on every phase of the Land Development Code update process to Land Development Code Update Steering Committee and Consultants | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Q3 2023 | Staff and/or volunteer time |
| Analyze new Land Development Code with regard to creation of affordable units and recommend best practices for Affordable Housing Overlay Zone and Shared Equity Ownership Models to address gaps as needed | Rebecca Buford & Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q3 2024 | Staff and/or volunteer time |
| Planned Strategy 4: Establish Tenant Legal Representation |  |  |  |
| Action Steps for Strategy 4: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Establish Tenant Legal Representation Workgroup | Human Services Program Manager | Q1 2023 | - |
| Identify funding partners | Tenant Legal Representation workgroup | Q4 2023 | Funding sources |
| Establish Tenant Legal Representation Pilot Project | Tenant Legal Representation workgroup | Q1 2023 |  |
| Propose Tenant Legal Representation ordinance based on outcomes of pilot | Tenant Legal Representation workgroup with community involvement | Q4 2024 | Community support |
| Planned Strategy 5: Establish source of income discrimination protection enforcement |  |  |  |
| Action Steps for Strategy 5: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Ensure passing of Source of Income discrimination protections | Source of Income workgroup, Human Relations Commission, City Staff | Q4 2023 |  |
| Work with Human Relations Commission, relevant City Staff, and City Commissioners to construct source of income discrimination investigation programming | Source of Income workgroup, Human Relations Commission, City Staff | Q4 2023 | Buy-in from all parties including Source of Income workgroup, Human Relations Commission, City Staff, and City Commissioners |
| Planned Strategy 6: Establish an ordinance, commonly known as a Vacant Structure Ordinance, which would allow the City of Lawrence to remediate the issue if a property is left vacant and uninhabited. |  |  |  |
| Action Steps for Strategy 6: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Research similar communities’ ordinances |  |  |  |
| Establish Vacant Structure Registry | City of Lawrence Code Official/Assistant Director of PDS | End Q4 2024 |  |
| Analyze Vacant Structure Registry and recommend Ordinance to City Commission | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | End of Q4 2025 |  |
| Identify plausible, appropriate enforcement policy/ordinance language | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | Q1 2026 | Sample language from reviewed policies Staff and/or volunteer time |
| Work with City Attorney’s Office to draft enforcement policy/ordinance change proposal | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | End of Q1 2026 | Buy-in from city codes enforcement and administration to revise the ordinances Staff and/or volunteer time |
| Submit policy/ordinance proposal to city legal counsel for review | City Legal Counsel, City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | Q2 2026 | Staff and/or volunteer time |
| Present enforcement policy/ordinance change proposal to the city commission for approval | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS | Q2 2026 | Staff and/or volunteer time |
| Planned Strategy 7: Establish an incentive program within City of Lawrence to encourage new affordable housing development |  |  |  |
| Action Steps for Strategy 7: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Research incentives for new affordable housing development, including waiving building and development review fees, providing property tax abatements for the creation of permanently affordable units, and expedited permitting. | City of Lawrence Affordable Housing Administrator, Affordable Housing Workgroup policy subcommittee | Q4 2023 | Staff time |
| Host forum with developers for recommendations and feedback. | Affordable Housing workgroup, Affordable Housing Workgroup policy subcommittee | Q12024 | Staff time, facilities, budget for catering and print materials |
| Develop initial recommendations on an affordable housing incentive program and present to the Lawrence City Commission for considerations. | Affordable Housing workgroup, Affordable Housing Workgroup policy subcommittee | Q2 2024 | Staff time |
| Further action steps dependent on Commission. |  |  |  |
| Planned Strategy 8: Create planned strategy for researching and acquiring funding resources (one-time and sustainable) |  |  |  |
| Action Steps for Strategy 8: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Develop a team to research grant opportunities. | Affordable housing grant team | Q1 2023 | Shared spreadsheet online for each team member to contribute details of 1) potential funders, 2) reasons they were selected as possibilities, 3) deadlines for proposals, 4) requirements of funder, 5) why specific funder would be appropriate/what outcomes and accountability (reporting) is required, and other information that will determine where applications are submitted. |
| Develop a plan for sharing the grant opportunities and supporting individuals, agencies, and government organizations in submitting grants. | Affordable housing grant team | Q2 2023 | Staff & or/ volunteer time Technology supports including software and other data management tools |
| Support grantees in implementation of programming as needed. | Affordable housing grant team | Ongoing | Staff & or/ volunteer time |
| Planned Strategy 9: Develop plan for ongoing community engagement to support affordable housing efforts |  |  |  |
| Action Steps for Strategy 9: |  |  |  |
| What is the action to be taken? |  |  |  |
| Plan and arrange at least 2 different community engagement meetings. Aim to draw more than 100 community members who are new to the issue of affordable housing. | Affordable Housing Workgroup subcommittee interested in panel and community engagement presentation and facilitation | Q1 2023 | Library resources, Would be good to involve AHAB Civic organizations and clubs Neighborhood associations Human Service agencies and stakeholders on panels and to function as facilitators |
| Get commitment from Local Human Service Providers to give PR for events and help tell the story about issues surrounding Affordable housing, through newsletters and social media and any other communication tools routinely used by providers | Affordable Housing Workgroup subcommittee | Q2 2023 Commitment by providers |  |
| Secure a local volunteer to lead PR promotions of affordable housing issues and events | Affordable Housing Workgroup subcommittee | Secure volunteer by Q2 2023 | Funds for print and other outreach materials |
| For subsequent years, plan for at least 1 annual community engagement affordable housing meeting. | Affordable Housing Workgroup subcommittee | Ongoing |  |
| Planned Strategy 10: Develop 10-year Community Housing Plan |  |  |  |
| Action Steps for Strategy 10: |  |  |  |
| What is the action to be taken? |  |  |  |
| Do updated housing assessment | Affordable Housing Workgroup & Consultant | Q2 2024 | Funds for consultants and assessments |
| Create and recommend schedule for ongoing housing assessments | Affordable Housing Workgroup & Consultant | Q2 2024 | Staff and /or volunteer time |
| Identify group to lead updated 10-year plan | Affordable Housing Workgroup & Consultant | Q3 2024 | Staff and /or volunteer time |
| Create action steps and timeline for new plan | Affordable Housing Workgroup & Consultant | Q3 2024 | Staff and /or volunteer time |
| Planned Strategy 11: Create permanent and sustainable diversified funding sources for the Affordable Housing Trust Fund |  |  |  |
| Action Steps for Strategy 11: |  |  |  |
| What is the action to be taken? |  |  |  |
| TBD |  |  |  |
| Planned Strategy 12: Develop targeted programs that increase racial equity in affordable housing access, and home and land ownership for Black, Indigenous People of Color experiencing housing disparities |  |  |  |
| Action Steps for Strategy 12: |  |  |  |
| What is the action to be taken? |  |  |  |
| TBD |  |  |  |
| Planned Strategy 13: Create increased opportunities for community ownership of land and property for low-income community members |  |  |  |
| Action Steps for Strategy 13: |  |  |  |
| What is the action to be taken? |  |  |  |
| Planned Strategy 14: Increase community capacity for permanent affordable housing development by identifying and supporting an additional Community Housing Development Organization (CHODO) and Community Land Trust |  |  |  |
| Action Steps for Strategy 15 |  |  |  |
| What is the action to be taken? |  |  |  |
| TBD |  |  |  |