| Housing Community Plan – Affordable Housing |  |  |  |
| --- | --- | --- | --- |
| Need: As of 2018 Lawrence housing market analysis 5,200 cost-burdened renters - 2,000 seniors - 1,500 persons with disabilities - 1,300 single mothers - 1,000 students 2,000 renters who want to buy & could be candidates for ownership. 700 families experiencing or at risk for homelessness. 500 households with disabilities with accessibility modification needs. 2,950 renters with units in poor condition 500 owners with units in poor condition |  | Objective(s): - By 2028, increase supply of affordable rental housing for households at 30-60%AMI by 1,500 new units. - increase supply of affordable units for households under 30%AMI by 375 (35%) new units - increase supply affordable units for households at 30-60%AMI by 1,125 (65%) new units - Of the above units, at least one-third will be 2-3 bedroom units - By 2028, increase supply of affordable homeownership housing for homeowners at 30-80%AMI by 200 new units - Increase supply of affordable HO units at 30-60% AMI by 100 (50%) - Increase supply of affordable HO unites at 60-80% by 100 (50%) - In the overall 200 units, increase supply of accessible, affordable units for seniors and people with disabilities at 30-80% AMI by 50. - Of the above units, 25% will be 4-5 bedroom units - By 2028, develop a 10-year affordable housing strategic plan - By 2028, establish system changes that realign power imbalances preventing access to, or development of, affordable housing |  |
| Planned Strategy 1: Provide grant subsidy for new development or rehab of units prioritized in objectives |  |  |  |
| Action Steps for Strategy 1: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Update AHTF NOFO & matrix to reflect priorities for 2-3 bedroom units that meet income targeting as identified in objectives | Lea Roselyn w/ Affordable Housing Advisory Board with community partners | Q1 2024 |  |
| Focused outreach with developers for discussions about incentives that would encourage/enable them to build units with 2-3 bedrooms and make at least 10% or more affordable. | Lea Roselyn w/ Affordable Housing Advisory Board with community partners | Q1 2024 | Staff and volunteer time Budget for print materials |
| Facilitate NOFO and grant allocation process with funding targeted to priorities as identified | Lea Roselyn w/ Affordable Housing Advisory Board with community partners | Q1 2024 & ongoing |  |
| Planned Strategy 2: Increase permanently affordable housing stock by identifying and acquiring parcels and units for the community land trust and future affordable housing development |  |  |  |
| Action Steps for Strategy 2: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Establish quarterly meetings with City of Lawrence Affordable Housing, Tenants to Homeowners/Community Land Trust, Habitat for Humanity, LDCHA and interested stakeholders to determine project priorities, acquisition opportunities, and partnership and project strategies | Lea Roselyn, Rebecca Buford, Erika Zimmerman, Shannon Oury | Q4 2023 |  |
| Research current City HOME & CDBG priorities | Lea Roselyn | Q4 2023 | Staff time |
| Identify additional on-going funding source | Lea Roselyn, Rebecca Buford, Erika Zimmerman, Shannon Oury | Q4 2023 | Staff time |
| Advocate for prioritization of locally allocated federal funds to be utilized for permanent affordability | Lea Roselyn, Rebecca Buford, Erika Zimmerman, Shannon Oury | Q1 2024 & ongoing | Staff and volunteer time |
| Acquire land & property for Trust using braided federal, state, local and private funding | Lea Roselyn, Rebecca Buford, Erika Zimmerman, Shannon Oury | Q1 2024 & ongoing | Staff and volunteer time |
| Planned Strategy 3: Provide recommendations to Land Development Code Update Steering Committee for code updates that allow for flexible, time-efficient and cost-effective affordable housing development. – |  |  |  |
| Action Steps for Strategy 3 |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Meet with Planning Director to gain understanding of Land Development Code update process, timing, and influence points | Rebecca Buford & Lea Roselyn, AHAB Subcommittee | Q1 2023 | Staff time |
| Determine the specific code updates to align for affordable housing land development code best practices (e.g. density, building typologies, ADUs, Shared Equity Ownership Models, etc.) | Rebecca Buford & Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q2 2023 | Staff and/or volunteer time |
| Provide input on Land Development Code update assessment | Rebecca Buford, Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q3 2023 | Staff and/or volunteer time |
| Write letter of recommended code updates to Land Development Code Update Steering Committee | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Q3 2023 | Staff and/or volunteer time |
| Regularly update Affordable Housing Workgroup on opportunities for ongoing engagement and communication for Land Development Code update | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Ongoing during Land Development Code update process (2023-2024) | Staff and/or volunteer time |
| Review and provide feedback on every phase of the Land Development Code update process to Land Development Code Update Steering Committee and Consultants | Rebecca Buford & Lea Roselyn with subcommittee of Affordable Housing Workgroup | Q3 2023 | Staff and/or volunteer time |
| Analyze new Land Development Code with regard to creation of affordable units and recommend best practices for Affordable Housing Overlay Zone and Shared Equity Ownership Models to address gaps as needed | Rebecca Buford & Lea Roselyn, with subcommittee of Affordable Housing Workgroup | Q3 2024 | Staff and/or volunteer time |
| Planned Strategy 4: Establish Tenant Right to Legal Representation in Douglas County |  |  |  |
| Action Steps for Strategy 4: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Establish Tenant Legal Representation Workgroup | Gabi Sprague, Human Services Program Manager | Q1 2023 | - |
| Identify funding partners | Tenant Legal Representation workgroup | Q4 2023 | Funding sources |
| Establish Tenant Legal Representation Pilot Project | Tenant Legal Representation workgroup | Q1 2023 |  |
| Propose Tenant Legal Representation ordinance based on outcomes of pilot | Tenant Legal Representation workgroup with community involvement | Q4 2024 | Community support |
| Planned Strategy 5: Establish source of income discrimination protection enforcement for City of Lawrence ordinance |  |  |  |
| Action Steps for Strategy 5: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Reconvene workgroup and identify detailed timeline & action strategies |  |  |  |
| Ensure passing of Source of Income discrimination protections | Gabby Boyle, Source of Income workgroup, Human Relations Commission, City Staff | Q4 2023 |  |
| Work with Human Relations Commission, relevant City Staff, and City Commissioners to construct source of income discrimination investigation programming | Source of Income workgroup, Human Relations Commission, City Staff | Q4 2023 | Buy-in from all parties including Source of Income workgroup, Human Relations Commission, City Staff, and City Commissioners |
| Planned Strategy 6: Establish a City of Lawrence vacant and dilapidated structure registry |  |  |  |
| Action Steps for Strategy 6: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Research similar communities’ ordinances | Lea Roselyn |  |  |
| Establish Vacant Structure Registry | Lea Roselyn with City of Lawrence Code Official/Assistant Director of PDS | End Q4 2024 |  |
| Analyze Vacant Structure Registry and recommend Ordinance to City Commission | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | End of Q4 2025 |  |
| Identify plausible, appropriate enforcement policy/ordinance language | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | Q1 2026 | Sample language from reviewed policies Staff and/or volunteer time |
| Work with City Attorney’s Office to draft enforcement policy/ordinance change proposal | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | End of Q1 2026 | Buy-in from city codes enforcement and administration to revise the ordinances Staff and/or volunteer time |
| Submit policy/ordinance proposal to city legal counsel for review | City Legal Counsel, City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS, Affordable Housing Workgroup policy subcommittee | Q2 2026 | Staff and/or volunteer time |
| Present enforcement policy/ordinance change proposal to the city commission for approval | City of Lawrence Affordable Housing Administrator, City of Lawrence Code Official/Assistant Director of PDS | Q2 2026 | Staff and/or volunteer time |
| Planned Strategy 7: Establish an incentive program within City of Lawrence to encourage new affordable housing development |  |  |  |
| Action Steps for Strategy 7: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Research incentives for new affordable housing development, including waiving building and development review fees, providing property tax abatements for the creation of permanently affordable units, and expedited permitting. | Lea Roselyn, Erika Zimmerman, City of Lawrence Affordable Housing Administrator, Affordable Housing Workgroup policy subcommittee | Q4 2023 | Staff time |
| Host forum with developers for recommendations and feedback. | Affordable Housing workgroup, Affordable Housing Workgroup policy subcommittee | Q12024 | Staff time, facilities, budget for catering and print materials |
| Develop initial recommendations on an affordable housing incentive program and present to the Lawrence City Commission for considerations. | Affordable Housing workgroup, Affordable Housing Workgroup policy subcommittee | Q2 2024 | Staff time |
| Further action steps dependent on Commission. |  |  |  |
| Planned Strategy 8: Create planned strategy for researching and acquiring funding resources (one-time and sustainable) |  |  |  |
| Action Steps for Strategy 8: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Develop a team to research grant opportunities. | Melissa Nolte & Lea Roselyn | Q32023 | Shared spreadsheet online for each team member to contribute details of 1) potential funders, 2) reasons they were selected as possibilities, 3) deadlines for proposals, 4) requirements of funder, 5) why specific funder would be appropriate/what outcomes and accountability (reporting) is required, and other information that will determine where applications are submitted. |
| Develop a plan for sharing the grant opportunities and supporting individuals, agencies, and government organizations in submitting grants. | Melissa Nolte & Lea Roselyn w/ Affordable housing grant team | Q2 2023 | Staff & or/ volunteer time Technology supports including software and other data management tools |
| Support grantees in implementation of programming as needed. | Melissa Nolte & Lea Roselyn w/ Affordable housing grant team | Ongoing | Staff & or/ volunteer time |
| Planned Strategy 9: Develop plan for ongoing community engagement to support affordable housing efforts |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Establish & convene affordable housing community engagement workgroup | Lea Roselyn, Gabi Sprague, Millie w/ workgroup | Q4 2023 |  |
| Plan and arrange at least 2 different community engagement meetings. Aim to draw more than 100 community members who are new to the issue of affordable housing. | Lea Roselyn, Gabi Sprague, Millie | Q1 2024 | Funding, space, facilitators, materials, childcare, food |
| Get commitment from Local Human Service Providers to give PR for events and help tell the story about issues surrounding Affordable housing, through newsletters and social media and any other communication tools routinely used by providers | Lea Roselyn, Gabi Sprague, Millie w/ workgroup | Q1 2024 Commitment by providers |  |
| Secure a local volunteer to lead PR promotions of affordable housing issues and events | Lea Roselyn, Gabi Sprague, Millie w/ workgroup | Q2 2024 | Funds for print and other outreach materials |
| For subsequent years, plan for at least 1 annual community engagement affordable housing meeting. | Lea Roselyn, Gabi Sprague, Millie w/ workgroup | Ongoing |  |
| Planned Strategy 10: Develop 10-year Community Housing Plan |  |  |  |
| Action Steps for Strategy 10: |  |  |  |
| What is the action to be taken? |  |  |  |
| Secure funding for updated assessment | Lea Roselyn & HID | Q4 2023 |  |
| Begin updated housing assessment | Lea Roselyn w Consultant | Q2 2024 | Funds for consultants and assessments |
| Community engagement on assessment | Lea Roselyn w/ affordable housing workgroup | Q3 2024 |  |
| Create and recommend schedule for ongoing housing assessments | Lea Roselyn w Consultant | Q4 2024 | Staff and /or volunteer time |
| Identify & convene group to lead updated 10-year plan | Lea Roselyn w/ affordable housing workgroup | Q1 2025 | Staff and /or volunteer time |
| Create action steps and timeline for new plan | Lea Roselyn w/ affordable housing workgroup | Q2 2025 | Staff and /or volunteer time |
| Planned Strategy 11: Create permanent and sustainable diversified funding sources for the Affordable Housing Trust Fund |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Convene AHAB subcommittee to research & advocate for additional revenue streams for the AHTF | Lea Roselyn & Monte Soukup & AHAB subcommittee | Q1 2024 | Staff & volunteer time |
| Research additional revenue streams for the AHTF | Lea Roselyn & Monte Soukup & AHAB subcommittee | Q1 2024 | Staff & volunteer time |
| Meet with CM office and commissioners on additional funding streams | Lea Roselyn & Monte Soukup & AHAB subcommittee | Q1 2024 | Staff & volunteer time |
| Identify priorities and feasibility for additional funding streams | Lea Roselyn & Monte Soukup & AHAB subcommittee | Q2-Q4 2024 | Staff & volunteer time |
| Recommend additional funding streams and based on recommendations outline additional action steps and timeline | Lea Roselyn & Monte Soukup & AHAB subcommittee | Q1 2025 | Staff & volunteer time |
| Planned Strategy 12: Develop targeted programs that increase racial equity in affordable housing access, and home and land ownership for Black, Indigenous People of Color experiencing housing disparities |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Create Restorative Housing Program Task Force or Reparations Council | Erika Zimmerman | Q1 2024 | Staff & volunteer time, funding |
| Research Restorative Housing programs, seeking best practices, what has worked and what hasn’t | Erika Zimmerman w/ Task Force | Q1-Q3 2024 | Staff & volunteer time |
| Hire consultant to assist in informing policies and procedure recommendations | Erika Zimmerman w/ Task Force | Q4 2024 | Staff & volunteer time |
| Engage Legal support and research | Erika Zimmerman w/ Task Force | Q4 2024 | Staff & volunteer time |
| Create and design the Restorative Housing Program | Erika Zimmerman w/ Task Force | Q1 2025 | Staff & volunteer time |
| Determine funding sources | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Determine goals of the program | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Determine activities of the program | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Determine parameters of the program | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Create strategies for distributing the reparations | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Create strategies for communication about the program | Erika Zimmerman w/ Task Force | Q1-Q2 2025 | Staff & volunteer time |
| Submit program design to legal counsel | Erika Zimmerman w/ Task Force | Q3 2025 | Staff & volunteer time |
| Present program to the City and County Commission | Erika Zimmerman w/ Task Force | Q3 2025 | Staff & volunteer time |
| Develop a homeownership (HO) education program focusing on creating access and opportunity to homeownership for black, and indigenous people of color | Erika Zimmerman w/ Task Force | Q1 2026 | Staff & volunteer time |
| Planned Strategy 13: Explore Increase community capacity for permanent affordable housing development by identifying and supporting an additional Community Housing Development Organization (CHODO) and Community Land Trust |  |  |  |
| What action is to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify organizations that meet the definition of Community Housing Development | Lea Roselyn, Erika Zimmerman, HID | Q2-Q4 2024 |  |
| Host information sessions to help orgs understand the expectations, benefits, and responsibilities of a CHODO | Lea Roselyn, Erika Zimmerman, HID | Q1 2025 |  |
| Assist organizations with applying for CHODO | Lea Roselyn, Erika Zimmerman, HID | Q1 2025 |  |
| Review HOME/CSBG dollars to figure out if there are opportunities for additional funding for CHODOs | Lea Roselyn, Erika Zimmerman, HID | Q1 2025 |  |
| Explore additional Community Land Trust opportunities | Lea Roselyn, Erika Zimmerman, HID | Q1 2025 |  |