## Sheet2
Priority Focus Area: |  | Equity & Inclusion
Related Objective(s): Note: Must follow SMART+C formatting; Include data source (currently available or to be developed); Include frequency of data reporting • Is there an opportunity to develop an objective that is related to achieving equity? • SMART+C: Specific, Measurable, Achievable, Relevant, Timed & Challenging" |  | 1. By 2024, develop operational goals of equity and inclusion within the lens of housing and homeless services to inform all areas of the Strategic Plan. 2. By 2025, ensure that data collection and performance assessments include meaningful measures that connect directly to equity goals with continuous feedback loops to ensure sustainability in the future. 3. By 2024, prioritize and embed equity goals within community education resources, communications, and events. Ensure continuing education of the strategic plan occurs throughout implementation and success of the plan highlighting Equity and Inclusion as a priority goal in all communication. 4. By 2024 Establish ongoing roles for diverse individuals with lived experience to inform and provide feedback to all areas of the strategic plan, as well as support the implementation of planned strategies. 5. By 2026, develop a decision making model that integrates equitable considerations– such as the distribution of funding–into policies, processes, procedures, and practices relating to homeless and housing services. 6. By 2026, identify policy and project initiatives aimed at increasing homeownership, building intergenerational equity, and improving housing retention for historically marginalized populations with a focus on Black/African-Americans and Native Americans. Increase accessibility in housing for persons with disabilities, and integrate accessible designs and principles in all new housing development projects within the Strategic Plan. 7. By 2027, create organizational assessments and supplemental training that encourages local agencies and government bodies to improve diversity and equity internally. Create a clear vision of communication and collaboration between all agencies, and provide resources to ensure an equitable lens in all areas of housing and homeless services that align with best practices that follow accessible sustainable housing and low barrier models.
Planned Strategy 1: Develop comprehensive terminology that informs strategic plan and supports shared vision of equity throughout all agencies and local governments.
Action Steps for Strategy 1:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Work with all focus area groups to gather terms needing to be defined and use definitions that are supportive to the topics of housing and homelessness | Equity & Inclusion Work Group | End of second quarter 2023 | Inter-Toolkit.pdf (iglyo.com) Definitions - City of Lawrence, Kansas (lawrenceks.org) examples of inclusive language e.g. First Nations or Native American Consider group/individual to review list
Planned Strategy 2: Establish and document four measures that connect directly to the strategic plan’s equity goals and advance system of care.
Action Steps for Strategy 2:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Create four system performance measures geared at reviewing and tracking equity outcomes by specific populations around affordable housing and homeless services (8 total measures). | KSHC Systems Workgroup Affordable Housing Workgroup State CoC Equity and Inclusion Workgroup | End of 3rd quarter 2023 | Data & Equity (tied to action)
Review current HMIS reports around services throughout Douglas County and system performance measures around the state (PIT, LSA, SPM) to determine disproportionalities within the system. | Work with Systems & Equity group to review data. If new data is needed or collected, determine where it should live (creation of dashboard). | End of 4th quarter 2023 | HMIS Team Support (Statewide) CES Team Support (Statewide) City and County Government IT (Dashboard development)
Review equity measurements, data reports and studies around affordable housing to determine disproportionalities around specific populations. | Affordable Housing Workgroup AHAB City of Lawrence, Douglas County
To establish accountability, present data across systems to ensure consistency and solicit feedback from both providers and lived experts. | Systems workgroup Equity & Inclusion Workgroup KSHC HSC Douglas County CoC | 2024
Collaboratively draft action plans or policies in response to any measure trending away from success, monitor progress making adjustments as needed. (e.g., if housing placements decrease over time, we as a system, will...) in both affordable housing and homeless services. | Housing and Homeless Stakeholders Group (Program managers) AHAB Lived Experience Advisory Board | 2025
Review 2018 housing study to determine disproportionalities within the community. Determine if it is appropriate to make a recommendation for an updated housing study. | Affordable Housing & Equity & Inclusion Work Group (potential addition to the dashboard recommend above). | 2023 | City and County Government IT (Dashboard development) City Affordable Housing Administrator (Lea Roselyn)
Planned Strategy 3: Prioritize and embed equity goals within community education resources, communications, and events. Ensure continuing education of the strategic plan occurs throughout implementation and success of plan highlighting Equity and Inclusion as a priority goal in all communication.
Action Steps for Strategy 3:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Community Listening session to discuss Equity and Inclusion Focus content of strategic plan | Equity & Inclusion Work Group | End of second quarter 2023
Evaluation of current community education & resources. Determine if new or updated resources are necessary to better communicate Equity and Inclusion. | Equity & Inclusion Work Group Service Agencies City & County | 2023 | Curriculum & Resources: Teaching for Racial Equity & Housing Justice ¦ Othering & Belonging Institute (berkeley.edu)
Plan a symposium on education for all agencies to better understand define shared vision and strategies. | Equity & Inclusion Work Group Service Agencies City & County | By year end of 2024
Make Easy Read versions of resources available to the community to support more equitable access for individuals who have language processing disabilities, speak English as a second language, and/or have brain injuries, as well as folks with other temporary or permanent disabilities that impact language processing. | Equity & Inclusion Work Group | 2024 | Autistic Self Advocacy Network: Guide to Making Easy Read Resources What Is Easy Read? - Photosymbols Also offers Foundation Course ($322) https://www.photosymbols.com/products/foundation-course Sample: Equity & Inclusion Strategic Plan
Planned Strategy 4: Establish ongoing roles for diverse individuals with lived experience to inform and provide feedback to all areas of the strategic plan, as well as support the implementation of planned strategies.
Action Steps for Strategy 4:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Create & implement compensation plan for folks with lived experience to participate in housing and homeless stakeholders group. | Equity & Inclusion Work Group Douglas County | 2023 | External sources/guides on compensation for community members. Alliance of unhoused neighbors HUD Exchange: Paying people with lived experience More examples of lived experience programs differentiated by focus populations; See program examples for women! Women’s safety has been highlighted a lot in feedback. Washington State Office of Equity: Compensation Plan Co-Design Process for Austin, TX
Require that all workgroups within the housing and homeless stakeholders have at least one member with lived experience to inform and provide feedback on implementation of plan. | Housing and Homeless Stakeholders Steering Committee | 2023 | Look into outreach/appointment ensuring an equitable approach
Creation of advisory board for folks with lived experience to inform and provide recommendation on all aspects of housing and homelessness | Equity & Inclusion Work Group Systems | 2024 | Resources to form a LEAB Lived experience advisory groups Baltimore City Baltimore LEAC booklet Washington State Office of Equity Co-Design Process for Austin, TX
Identify facilitators and resources to support ongoing, frequent community engagement sessions for all folks currently experiencing homelessness | Equity & Inclusion Workgroup Lived Experience members, paid roles Other community partners as requested and available | 2024
Planned Strategy 5: To ensure equitable access to funding, policy and procedure initiatives specific to homeless and housing agencies, develop and implement decision making models with a target on reducing disparities for marginalized populations.
Action Steps for Strategy 5:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Support the creation and implementation of a Budget Equity Assessment Tool for equitable distribution of funding | City/County Equity & Inclusion Work Group | 2025-26 | San Antonio, Portland, Dunham County
Oversee the prioritization of funding, resources and outreach for affordable housing and supportive housing projects to ensure an equity focus. Make recommendations as needed. | Affordable Housing Supportive Housing Equity & Inclusion Work group CoC | Beginning 2023 | **Real Estate Development & Initiatives JoCo Housing Study (see ordinance review checklist) Case Studies: Best Practices in Tribal Housing Vernacular Housing Partnering Affordable Housing w/ Indigenous Communities More Co-ops, communal housing options; embedding community input into housing development planning, equity lens
Planned Strategy 6: Identify major policy and project initiatives that ensure equitable access in housing and homeless services by specifically addressing and supporting restorative housing programs, development projects geared toward accessibility and strategies that support in sustaining housing reducing the risk of homelessness.
Action Steps for Strategy 6:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Research and develop a plan for a local reparation program to address racial disparities within Douglas County | Equity & Inclusion Workgroup (support research phase) City/County (continued research & implementation) | Beginning 2024 | Affordable Housing as Local Reparations for Black Americans: Case Studies ¦ Othering & Belonging Institute (berkeley.edu) with suggested partnership: Haskell University City of Evanston
Support changes to zoning policies for more inclusive and integrated communities | in progress at the City & County level | 2024 | How Minneapolis became the first to end single-family zoning See also: DgCo Climate Action Plan, sections on equitable & affordable housing
Support nondiscrimination policies that protect renters/buyers from discrimination based on source of income, immigration status, and criminal history | in progress at city level (SOI, immigration status) in progress at HRC (criminal history) | 2024 | Examples of Fair Chance Ordinances for limiting the use of criminal records in prospective tenant screening San Francisco, Richmond, Cook County, New Jersey
Recommend requiring universal design in new housing construction projects for affordable and supportive housing | Affordable Housing Supportive Housing Affordable Housing Trust Fund City/County | Beginning 2023, recommend considerations when funding new construction projects Policy implementation 2025 | Universal Design, defined Affordable Housing Commission of the City of St. Louis - Universal Design Requirements for all new construction projects Case studies regarding housing, access, and dementia (p. 148-161) Wounded Warrior Home Project (vets with physical disabilities and PTSD) Johnson County, KS received recommendations for Universal Design in housing development >>More case studies from JOCO website More examples from NLIHC Study of Accessibility and Universal Design in Affordable Housing
Recommend strengthening or developing additional direct financial assistance program and other direct assistance programs aimed at preventing homelessness for focus populations with heightened risks | Make a list of providers currently offering direct financial assistance in homelessness prevention (rental assistance, utility assistance, etc.) | 2025 | https://fr.bfzcanada.ca/wp-content/uploads/Microsoft-Word-evidence-page-prevention-10.29.18rev-opt2.pdf https://www.homelesshub.ca/blog/homelessness-prevention-public-health-model covers the topic of homelessness be a public health problem
Planned Strategy 7: Create organizational assessments and supplemental training that encourages local agencies and government bodies to improve diversity and equity internally. Create a clear vision of communication and collaboration between all agencies, and provide resources to ensure an equitable lens in all areas of housing and homeless services that align with best practices that follow accessible sustainable housing and low barrier models.
Action Steps for Strategy 7:
What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed?
Recommend seeking to increase diversity in hiring practices (i.e. advertising in non- traditional places, including interview questions that discuss equity) | Housing and Homeless Service Providers City/County Homeless & Housing Departments | 2023 | 2022 CoC on Centering Racial Equity Haskell Career Fair
Recommend increased outreach and collaboration between social service providers, city/county leaders, and organizations with expertise on focus populations | Diversity & Equity Workgroup (outreach) Social service providers, city and county government individually responsible for implementing practices | 2023 | *Include in planned symposium for service providers (see above) Collaborate with… Haskell University Haskell Indian Health Center KU (equity departments) Independence Inc Minds Matter Community Groups
Create list of recommendations & resources agencies may use to encourage more equitable practices within their organization | Diversity & Equity Workgroup | 2024 | Find more on racialequitytools.org Internally assess & revise current DEI strategy Why it’s important to practice antiracism Intersectionality Toolkit LAHSA report & recommendations of Ad Hoc Committee on black people experiencing homelessness (2018)
Recommend low barrier practices in emergency services to reduce barriers that cause disparities in equity | Emergency Services workgroup Equity & Inclusion Work Group | 2024 | Emergency Shelter Learning Series Low-Barrier Playlist Understanding Low Barrier Shelter, Philosophy Matrix Indianapolis Case Study
Promote LGBTIQ+ inclusive and gender-affirming policies, staff training, and service programs | Emergency Services workgroup Equity & Inclusion Work Group | 2023 (Ongoing) | Best Practices for LGBTQ, Cultural Competency Training [sample training plans]