| Focus Area Content |  |  |  |
| --- | --- | --- | --- |
| Priority Focus Area: |  | Supportive Housing |  |
| Related Objective(s): Note: Must follow SMART+C formatting; Include data source (currently available or to be developed); Include frequency of data reporting - Is there an opportunity to develop an objective that is related to achieving equity? |  | - By 2027 increase the number of permanent supportive housing units dedicated to chronically homeless individuals by 30 in Douglas County - By 2027 increase the number of permanent supportive housing units dedicated to chronically homeless families by 2 (100%) - By 2027 increase the number of permanent supportive housing units dedicated to homeless nearly elderly, 55+ individuals by 50 units - By 2027 increase the number of permanent supportive housing units dedicated to justice-involved individuals by 20 in Douglas County - By 2027 increase the number of transitional housing units dedicated to homeless individuals with SUD and/or mental illness by 15 in Douglas County - By 2027 increase the number of transitional housing units dedicated to homeless families with SUD and/or mental illness by 10 in Douglas County - By 2027 increase the number of transitional housing units dedicated to homeless, child-welfare involved families by 10 |  |
| Planned Strategy 1: Develop a 5-year Supportive Housing Capital Improvement Plan (CIP) that reflects supportive, trauma informed housing design and community integration. Note: this should include capital and operative budgets |  |  |  |
| Action Steps for Strategy 1: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Design and develop plan for permanent supportive housing capital asset(s) acquisition and development | Capital Acquisitions and Development workgroup | End of 3rd quarter 2023 | Organizational commitments, staff time |
| Design and develop plan for transitional supportive housing capital asset(s) | Capital Acquisitions and Development workgroup | End of 3rd quarter 2023 | Organizational commitments, staff time |
| Design and develop transitional family housing capital asset(s) | Family Supportive Housing and Sheltering workgroup | End of 2nd of quarter 2023 | Organizational commitments, staff time |
| Advocate and engage with Lawrence-Douglas County Planning and Zoning to address land use, zoning, and code improvements needed to support capital asset development (mixed use, higher density, etc.) | City/County Planning and Zoning and Capital Acquisitions and Development workgroup | End of 1st quarter 2023 | Organizational commitments, staff time |

| Planned Strategy 2: Establish a community supportive housing case management program based on evidenced based practices |  |  |  |
| --- | --- | --- | --- |
| Action Steps for Strategy 2: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Define community wide standards and definitions for case management and case managers for low-barrier supportive housing -housing readiness | Low-Barrier Housing Case Management workgroup | End of 1st quarter 2023 | Organizational commitments, staff time, potential consulting or research fees/costs |
| Identify lead agencies and develop programming and MOU’s | Low-Barrier Housing Case Management workgroup and City/County Management | End of 2nd quarter 2023 | Organizational commitments, financial resources will be needed to fund potential solutions (staffing, operating expenses, etc.) |
| Develop a network of providers to promote long-term housing (to include financial literacy, legal assistance, life skills, employment, etc.). | Lawrence Douglas County Housing Authority (resident services), Kansas Legal Services and Kansas Workforce Center | End of 2nd quarter 2023 | Organizational commitments, staff time, financial resources will be needed for staff and programming. |
| Planned Strategy 3: Establish sustainable public and private operating and supportive services funding resources |  |  |  |
| Action Steps for Strategy 3: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify lead agency or agencies to apply for and manage annual and special NOFO funding | Douglas County Administrator’s Office | End of 2nd quarter 2023 | Organizational commitments, staff time |
| Establish a locally funded flexible housing subsidy pool program to scale and sustain supportive housing operations and services | Douglas County Administrator’s Office and Lawrence Douglas County Housing Authority | Beginning of 4th quarter 2023 | Financial resources for programming and staff, organizational commitment, staff time |
| Identify one-time and ongoing private/non-profit funding sources and partnership | Fund Research and Development group | End of 2nd quarter 2023 | Staff time |
| Establish outcomes and key performance indicators | Housing & Homeless Stakeholder Group | December 2023 | Staff time, potential consulting or research fees |
| Planned Strategy 4: Design and develop emergency, non-congregate shelter services for women, families and disabled single adults Note: This is a temporary strategy while transitional and permanent supportive housing units are under development, but some amount of emergency shelter should always be available for this population. |  |  |  |
| Action Steps for Strategy 4: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Inventory existing congregate and non-congregate emergency sheltering resources for women, families and disabled single adults. | Family Supportive Housing and Sheltering workgroup | End of first quarter 2023 | Staff time, potential consulting or research fees |
| Planned Strategy 5: Design a community outreach and communications curriculum to build community buy-in, trust, and engagement in supportive housing |  |  |  |
| Action Steps for Strategy 5: |  |  |  |
| What is the action to be taken? | Who is responsible? | By when will it be complete? | What resources or supports are needed? |
| Identify evidence-based practices essential to service models for supportive housing: housing first, harm reduction, trauma informed care, motivational interviewing, etc. | Advocacy and education Committee | End of 2nd quarter 2023 | Staff time, potential consulting or research fees, particularly to engage community members with lived experience |
| Develop community training and education sessions on supportive housing design and community integration from which the community may benefit | Advocacy and education Committee | End 2nd quarter 2023 | Staff time, potential consulting or research fees, particularly to engage community members with lived experience |